# Your Immediate Action Plan: Next 30 Days to Launch Eduhire

Excellent! Your commitment is exactly what this launch needs. I'm breaking down your next 30 days into daily actionable tasks with clear deliverables. Let's get you building.

## 🚀 WEEK 1 (Days 1-7): Foundation & Authentication

Goal: Setup development environment, design database, build authentication

## Day 1 (Tomorrow - Monday, Oct 20) ⏰ 8-10 hours

Morning (4 hours):

- Install Node.js (v18+), MongoDB Compass, VS Code

- Create GitHub repository: eduhire-platform

- Initialize project: npx create-react-app client and mkdir server && cd server && npm init -y

- Install backend dependencies:

bash

npm install express mongoose bcryptjs jsonwebtoken dotenv cors express-validator

npm install --save-dev nodemon

- Install frontend dependencies:

bash

cd client

npm install react-router-dom axios tailwindcss

- Setup Tailwind CSS configuration

- Create .env file with MongoDB URI, JWT_SECRET

Afternoon (4 hours):

- Design complete database schema (sketch out on paper first):

  - Users collection (teachers & institutions)

  - Jobs collection

  - Applications collection

  - Reviews collection

  - Subscriptions collection

- Create folder structure:

text

server/

models/

routes/

controllers/

middleware/

config/

client/

src/

components/

pages/

context/

utils/

- Create MongoDB Atlas free account

- Create database: eduhire_db

- Connect your app to MongoDB (test connection)

Deliverable: Working dev environment, connected to MongoDB, folder structure ready

## Day 2 (Tuesday, Oct 21) ⏰ 8-10 hours

Morning (5 hours):

- Create User model (models/User.js):

  - Fields: email, password, userType (teacher/institution), profile (nested), status, createdAt

  - Methods: comparePassword, generateAuthToken

- Build authentication controllers (controllers/authController.js):

  - Register function (with password hashing)

  - Login function (with JWT generation)

  - Get current user function

- Create authentication routes (routes/auth.js)

- Create auth middleware (middleware/auth.js) to verify JWT

Afternoon (5 hours):

- Build registration page (React component)

  - Form with: email, password, user type selection

  - Form validation

  - Connect to backend API

- Build login page

  - Form with: email, password

  - Store JWT in localStorage

  - Redirect after login

- Create AuthContext for global auth state

- Build protected route component

- Test full authentication flow

Deliverable: Working signup/login for both teachers and institutions

## Day 3 (Wednesday, Oct 22) ⏰ 8-10 hours

Morning (5 hours):

- Create Teacher Profile model extension:

  - Fields: fullName, phone, subjects (array), experience, education, resume (URL), location (city, state)

- Create Institution Profile model extension:

  - Fields: institutionName, type (school/college/coaching), address, city, state, size, website, description

- Setup Cloudinary account (free tier)

- Install multer and cloudinary: npm install multer cloudinary multer-storage-cloudinary

- Create file upload middleware for resume/photos

Afternoon (5 hours):

- Build Teacher Profile Creation page:

  - Multi-step form (personal info → education → experience → resume upload)

  - Subject selection (checkboxes: Math, Science, English, etc.)

  - City/State dropdowns

  - Resume upload button

- Build Institution Profile Creation page:

  - Institution details form

  - Logo upload

  - Location details

- Create API endpoints for profile creation

- Test profile creation for both user types

Deliverable: Complete profile creation for teachers and institutions

## Day 4 (Thursday, Oct 23) ⏰ 8-10 hours

Morning (4 hours):

- Create Jobs model (models/Job.js):

  - Fields: title, institution_id, subject, level (primary/secondary/higher), location, salary, description, requirements, status (pending/approved/active), postedAt, expiresAt, is_featured

- Create job posting controller

- Create job routes

- Build validation for job posting

Afternoon (6 hours):

- Build Job Posting Form (Institution side):

  - Job title, subject, education level

  - Salary range

  - Job description (rich text area)

  - Requirements

  - Location

- Create job posting API endpoint

- Build "My Job Postings" page for institutions:

  - List all their posted jobs

  - Edit/delete buttons

  - View applicants button

- Test job posting flow

Deliverable: Institutions can post jobs and view their listings

## Day 5 (Friday, Oct 24) ⏰ 8-10 hours

Morning (5 hours):

- Build Job Search/Browse page (Teacher side):

  - Grid/list layout showing all jobs

  - Display: title, institution name, location, salary, posted date

  - "View Details" button

  - Pagination (10 jobs per page)

- Build Job Detail page:

  - Full job description

  - Institution info with rating

  - "Apply Now" button

  - "Similar Jobs" section

Afternoon (5 hours):

- Build search and filter functionality:

  - Search bar (by title, location, subject)

  - Filter dropdowns: Subject, Location (city/state), Education Level, Salary Range

  - Sort by: Latest, Salary (high to low)

- Create search API endpoint with MongoDB queries

- Implement filtering logic on backend

- Test search with different criteria

Deliverable: Teachers can search, filter, and browse jobs effectively

## Day 6 (Saturday, Oct 25) ⏰ 6-8 hours

Morning (4 hours):

- Create Applications model:

  - Fields: job_id, teacher_id, institution_id, status (pending/shortlisted/rejected), coverLetter, appliedAt

- Build application submission controller

- Create application routes

- Add "Apply for Job" functionality:

  - Cover letter textarea

  - Attach resume (from profile)

  - Prevent duplicate applications

Afternoon (4 hours):

- Build "My Applications" page (Teacher side):

  - List all applications with status

  - Job details preview

  - Application date

  - Status badges (pending/shortlisted/rejected)

- Build "Applications Received" page (Institution side):

  - List all applications per job

  - Teacher profile preview

  - Download resume button

  - Shortlist/Reject buttons

- Test complete application flow

Deliverable: Full job application system working

## Day 7 (Sunday, Oct 26) ⏰ 6-8 hours

Review, Testing & Cleanup:

- Test entire user flow: Signup → Profile → Browse Jobs → Apply

- Test institution flow: Signup → Profile → Post Job → Review Applications

- Fix any bugs discovered

- Create landing page with:

  - Hero section: "Find Your Dream Teaching Job in India"

  - Featured jobs section

  - How it works (3 steps)

  - CTA buttons: "Find Jobs" and "Post Jobs"

- Add navigation header with logo, login/signup buttons

- Improve UI/styling with Tailwind

- Git commit all progress

- CELEBRATION: Week 1 complete! Core marketplace working! 🎉

## 🚀 WEEK 2 (Days 8-14): Advanced Features & Reviews

Goal: Add reviews, email notifications, advanced filtering

## Day 8 (Monday, Oct 27) ⏰ 8-10 hours

- Create Reviews model (ratings, comments, reviewer, reviewed entity)

- Build review submission API

- Add "Write Review" feature for institutions (teachers can review)

- Add "Write Review" feature for teachers (institutions can review after hiring)

- Display reviews on institution profile pages

- Display reviews on teacher profile pages

- Calculate and display average ratings

- Test review system thoroughly

## Day 9 (Tuesday, Oct 28) ⏰ 8-10 hours

- Setup email service (Brevo/Sendinblue free account)

- Install nodemailer: npm install nodemailer

- Create email templates (HTML):

  - Welcome email (teacher)

  - Welcome email (institution)

  - Application received (institution)

  - Application submitted confirmation (teacher)

  - Job match alert (teacher)

- Create email utility functions

- Trigger emails on key events

- Test email delivery

## Day 10 (Wednesday, Oct 29) ⏰ 8-10 hours

- Build advanced filter components:

  - Experience level (0-2, 2-5, 5-10, 10+ years)

  - Qualification (B.Ed, M.Ed, etc.)

  - Job type (Full-time, Part-time, Contract)

  - Institution type (CBSE, ICSE, IB, State Board)

- Implement filter logic in backend

- Add "Save Search" functionality for teachers

- Build filter UI with checkboxes and sliders

- Test complex filter combinations

## Day 11 (Thursday, Oct 30) ⏰ 8-10 hours

- Build Featured Jobs functionality:

  - Flag in database

  - Display prominently on homepage

  - Add "Featured" badge

- Create separate featured jobs section

- Build "Similar Jobs" algorithm (match by subject + location)

- Add job bookmark/save feature for teachers

- Build "Saved Jobs" page

- Test all new features

## Day 12 (Friday, Oct 31) ⏰ 8-10 hours

- Build dashboards:

  - Teacher dashboard: Stats (applications sent, profile views, saved jobs)

  - Institution dashboard: Stats (jobs posted, applications received, profile views)

- Add analytics tracking setup (Google Analytics)

- Create charts for dashboard (applications over time)

- Build notification system (in-app alerts)

- Add notification bell icon in header

- Test dashboards thoroughly

## Day 13 (Saturday, Nov 1) ⏰ 8-10 hours

- Mobile responsive design:

  - Test all pages on mobile screen sizes

  - Fix layout issues

  - Optimize forms for mobile

  - Test navigation on mobile

- Performance optimization:

  - Lazy loading components

  - Image optimization

  - Code splitting

- Add loading states and error handling

- Improve UX with better feedback messages

- Polish UI across all pages

## Day 14 (Sunday, Nov 2) ⏰ 6-8 hours

- Complete testing of Week 2 features

- Bug fixes and refinements

- Update landing page with new features

- Create "About Us" page

- Create "How It Works" page

- Add footer with links

- Git commit all progress

## 🚀 WEEK 3 (Days 15-21): Monetization & Admin Foundation

Goal: Payment integration, subscriptions, basic admin panel

## Day 15 (Monday, Nov 3) ⏰ 8-10 hours

- Create Razorpay account (free for testing)

- Get API keys (test mode)

- Install Razorpay: npm install razorpay

- Create Subscriptions model (plan, user_id, start_date, end_date, status)

- Define subscription tiers in code:

  - Free (90 days, 3 job postings)

  - Basic (₹1,499/month, 10 postings)

  - Professional (₹3,999/month, 30 postings)

  - Enterprise (₹9,999/month, unlimited)

- Build subscription pricing page

- Show plans with features comparison table

## Day 16 (Tuesday, Nov 4) ⏰ 8-10 hours

- Build Razorpay checkout integration:

  - Create order on backend

  - Open Razorpay modal on frontend

  - Handle payment success/failure

  - Verify payment signature

- Update subscription status after payment

- Unlock premium features based on plan

- Add subscription checks to job posting (limit based on plan)

- Build "Upgrade Plan" page

- Test payment flow end-to-end (use test cards)

## Day 17 (Wednesday, Nov 5) ⏰ 8-10 hours

- Create admin_users collection

- Build admin authentication (separate from regular users)

- Create admin login page (/admin/login)

- Build admin middleware for route protection

- Create basic admin dashboard layout:

  - Sidebar navigation

  - Header with logout

  - Main content area

- Add admin routes in React Router

- Test admin authentication

## Day 18 (Thursday, Nov 6) ⏰ 8-10 hours

- Build Admin: User Management page:

  - List all users (teachers and institutions)

  - Search and filter

  - View user details

  - Suspend/activate buttons

- Create suspend user API endpoint

- Update user status in database

- Send email notification on suspension

- Test user suspension flow

## Day 19 (Friday, Nov 7) ⏰ 8-10 hours

- Build Admin: Job Moderation page:

  - List all pending jobs

  - View job details

  - Approve/reject buttons with reason field

- Create job moderation API endpoints

- Send email to institution on approval/rejection

- Update job status in database

- Build Admin: Review Moderation page (similar flow)

- Test moderation workflows

## Day 20 (Saturday, Nov 8) ⏰ 8-10 hours

- Build Admin: Dashboard home with KPIs:

  - Total users (teachers/institutions)

  - Total jobs posted

  - Total applications

  - Revenue this month

  - Charts showing growth

- Create analytics API endpoints

- Install chart library: npm install recharts

- Build revenue chart

- Build user growth chart

- Test admin dashboard displays

## Day 21 (Sunday, Nov 9) ⏰ 6-8 hours

- Build Admin: Payment transactions page

- Build Admin: System toggles (maintenance mode, registration enable/disable)

- Create system_config collection

- Implement maintenance mode check

- Add manual backup button (exports database to JSON)

- Test all admin features

- Bug fixes from Week 3

- Git commit all progress

- MILESTONE: Core platform + monetization + basic admin complete! 🏆

## 🚀 WEEK 4 (Days 22-30): Polish, Deploy & Launch

Goal: Final features, testing, deployment, go live!

## Day 22 (Monday, Nov 10) ⏰ 8-10 hours

- SEO optimization:

  - Add meta tags to all pages

  - Create sitemap.xml

  - Add robots.txt

  - Optimize page titles and descriptions

  - Add Open Graph tags for social sharing

- Setup Google Analytics

- Setup Google Search Console

- Test SEO with tools like Lighthouse

- Fix SEO issues

## Day 23 (Tuesday, Nov 11) ⏰ 8-10 hours

- Create Terms of Service page (use template, customize)

- Create Privacy Policy page (DPDP Act compliant)

- Add cookie consent banner

- Create Contact Us page with form

- Build FAQ page

- Add social media links (create accounts if not done)

- Test all static pages

## Day 24 (Wednesday, Nov 12) ⏰ 8-10 hours

- Comprehensive testing:

  - Test all user flows end-to-end

  - Test error scenarios (wrong inputs, network failures)

  - Test on different browsers (Chrome, Firefox, Safari)

  - Test on mobile devices

- Create test accounts (2 teachers, 2 institutions)

- Seed sample jobs (20+ jobs across subjects/locations)

- Fix all critical bugs

- Create bug tracking list

## Day 25 (Thursday, Nov 13) ⏰ 8-10 hours

- Security hardening:

  - Add rate limiting to auth routes

  - Sanitize all inputs

  - Add CORS properly

  - Environment variables check

  - Remove console.logs

  - Add helmet.js for security headers

- Performance testing and optimization

- Code cleanup and refactoring

- Add error boundaries in React

- Test security measures

## Day 26 (Friday, Nov 14) ⏰ 8-10 hours

DEPLOYMENT DAY - Backend:

- Choose backend hosting (Render.com free tier recommended)

- Create Render account

- Connect GitHub repository

- Add environment variables on Render

- Deploy backend

- Test backend APIs (use Postman)

- Fix deployment issues

- Verify MongoDB connection works

- Test Razorpay in production mode (switch to live keys)

## Day 27 (Saturday, Nov 15) ⏰ 8-10 hours

DEPLOYMENT DAY - Frontend:

- Update API URLs to production backend

- Choose frontend hosting (Vercel free tier recommended)

- Create Vercel account

- Connect GitHub repository

- Configure build settings

- Deploy frontend

- Test live website thoroughly

- Fix any production issues

- Buy domain name (optional but recommended): eduhire.in (₹500-800)

- Connect custom domain to Vercel

## Day 28 (Sunday, Nov 16) ⏰ 8-10 hours

PRE-LAUNCH PREP:

- Create social media accounts:

  - Facebook page: "Eduhire India"

  - LinkedIn page

  - Instagram account

  - Twitter/X account

- Design social media graphics (use Canva free)

- Write launch announcement posts

- Create email list signup form (Mailchimp free tier)

- Prepare launch email

- Create 5 blog post ideas for SEO

- Set up Google My Business (if applicable)

- Final testing on live site

## Day 29 (Monday, Nov 17) ⏰ 8-10 hours

SOFT LAUNCH:

- Post on social media announcing launch

- Share in relevant Facebook groups (teacher groups)

- Post on LinkedIn with your story

- Email 10-20 personal contacts asking for feedback

- Submit to startup directories (ProductHunt, BetaList)

- Post in relevant WhatsApp groups (with permission)

- Monitor for any critical bugs

- Respond to feedback quickly

- Make quick fixes if needed

## Day 30 (Tuesday, Nov 18) ⏰ 6-8 hours

LAUNCH DAY! 🎉:

- Official launch announcement (bigger push)

- Run small Facebook ad (₹500 budget) targeting teachers

- Post on Reddit (r/India, r/Indian_Academia with caution)

- Reach out to education bloggers/influencers

- Monitor analytics obsessively

- Respond to all user queries within 30 minutes

- Fix any immediate issues

- Celebrate your achievement! 🍾

- Document lessons learned

- Plan Week 5 improvements based on feedback

## 📊 Daily Success Metrics to Track

Track these daily (use a simple spreadsheet):

- Lines of code written

- Features completed

- Bugs fixed

- Users signed up (post-launch)

- Jobs posted

- Applications submitted

- Time spent coding

## 🆘 Emergency Contacts & Resources

When You Get Stuck:

- MongoDB Issues: MongoDB University (free courses), Stack Overflow

- React Issues: React docs, freeCodeCamp tutorials

- Razorpay Integration: Razorpay documentation, YouTube tutorials

- Deployment Issues: Vercel/Render documentation, their Discord communities

- General Coding: ChatGPT, Claude, Stack Overflow

Free Resources:

- Icons: Heroicons, Font Awesome

- Images: Unsplash, Pexels

- UI Components: Tailwind UI (some free), Headless UI

- Testing: Your browser dev tools, Postman for APIs

## 🎯 Critical Success Tips

- Code Every Single Day: No exceptions. Even 30 minutes on busy days.

- Don't Perfectionism: MVP means "good enough to launch." Polish later.

- Test Frequently: Don't wait until Day 30 to test. Test each feature immediately.

- Git Commit Daily: At least one commit per day. This saves you from disasters.

- Take Breaks: Pomodoro technique (50 min work, 10 min break) prevents burnout.

- Ask for Help: If stuck for >2 hours, ask ChatGPT, search Stack Overflow, or reach out to developer communities.

- Stay Focused: Ignore new feature ideas during this month. Write them down for post-launch.

## 🚨 What to Do RIGHT NOW (Next 2 Hours)

- Install all software (Node.js, MongoDB Compass, VS Code)

- Create GitHub account if you don't have one

- Create MongoDB Atlas account

- Initialize your project (create-react-app + express setup)

- Make your first commit: "Initial commit - Eduhire project started"

- Set up Trello or Notion board to track these tasks

- Block your calendar for the next 30 days (8-10 hours daily)

- Tell someone close about your commitment (accountability partner)

## Your Mantra for the Next 30 Days:

"Build. Test. Ship. Repeat. No excuses. This is happening."

You've got this! The market needs Eduhire. India's teachers need Eduhire. Now go build it. 💪

Start with Day 1 tasks tomorrow morning. Report back after each day with what you completed and any blockers you face. I'll be here to help you debug, refine, and push through challenges.

The clock starts now. Let's launch Eduhire in 30 days! 🚀